## Working route
Blackboard Group No 01 Class NII | Project kickoff |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Final Submit (and version 3 Pro option)
SMART goals ==> | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP
hide this row after inputting class date |  | PM class date | =====> | 2022-03-29 |  |  |  | PM class date plus | 8 | days |  |  | PM class date plus | 13 | days |  |  | PM class date plus | 14 | days | Last possible submit date: | 2022-04-12 | PM class plus | 14 | days
Each group member | Project Mgmt Activity | share with team | 1 | Wednesday Mar.30 | TO DO
Group Meeting Agenda ==> | create MS Team Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to group members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 | Thursday Mar.31 | TO DO | review progress, refine plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. |  | Sunday Apr.3 | TO DO | Group decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Friday Apr.8 | TO DO | Group decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Saturday Apr.9 | TO DO | Submit final version of artefacts from Teams to Blackboard. Backup Teams files. | updated DONE items below with actual hours. |  | Saturday Apr.9 | TO DO
Lathesan (Fundamentals) | Create Folders in local folders containing original documents and version folders | Deliverable is measured if: I have created a Local folder and have begun prepping folders for the various Version | Planned Hours: 1.5 [Actual Hours: 2.5] | Thursday Mar.31 | Done on Time | * Complete Version 1 of Fundamentals.c & Fundamentals.h. Review and compile with Team once completed. Add comments to explanain how code works. | deliverable is measured: once Hesam comments on the file and the users take the input and make changes to program. Delivery Criteria is agreed if Hesam is able to comment on file and changes are able to be made | Planned Hours: 3.0 [Actual Hours: 2.5] | Monday Apr.4 | Done on Time | * make changes to Version 1 of Fundamentals.c & Fundamentals.h. Review and compile with Team once completed. Save in group Folder under Version 2. Add comments on changes made in second version. | Tasks have been assigned and all members have agreed to deliver on stated due date aswell and update status as needed. | Planned Hours: 3.0 [Actual Hours: ???] | Saturday Apr.9 | To Do | * make changes to Version 2 of Fundamentals.c & Fundamentals.h. Review and compile with Team once completed. Save in group Folder under Version 3. Add comments on changes made in third version. | Tasks have been assigned and all members have agreed to deliver on stated due date aswell and update status as needed. | Planned Hours: 3.0 [Actual Hours: ?.?] | Sunday Apr.10 | To Do | * make changes to Version 3 of Fundamentals.c & Fundamentals.h. Review and compile with Team once completed. Save in group Folder under Version 3.9. Add comments on changes made in third final version. Submit To team leader, and ask Team leader to Back Up Teams files. Create a New Pro Version of Version 3 and call it Pro Version 1 with required features and submit as well after checks. | If Version 3 is updated to 3.0, uploaded to Blackboard and if all statuses are set to done. All items are reviewed and uploaded aswell as create a pro version and submit. | Planned Hours: 5.0 [Actual Hours: ?.?] | Monday Apr.11 | To Do
Henly (Manipulating) | Create folders for the different versions in local folders. To store the original documents and the different versions of the document. | Deliverable is measurd: if I have created folders in the local folders to house the original documents and the different versions of the documents. | Planned Hours: 1.5 [Done in 1 hour] | Thursday Mar.31 | Done on time | Complete Version 1 of manippulating.c & manipulating.h. Review and compile with Team once completed. Add comments to explanain how code works. | Deliverable is measured: When the files submitted are working. The delivery criteria is agreed when we have completed our work and there is nothing left to do. | Planned Hours: 2.0[Done in 1.5] | Monday Apr.4 | Done | Make changes to version one of manipulating.c and manipulating.h. Review with team once the changes have been made. Save file under version 2 folder. | Delivery is measured: when everyone submits their code by the deadline. The delivery criteria is agreed when we don't have anything else to do. | Planned for 3 hours | Saturday Apr.9 | To Do | Make changes to version two of manipulating.c and manipulating.h. Review with team once the changes have been made. Save file under version 3 folder. | Delivery is measured: when everyone submits their code by the deadline. The delivery criteria is agreed when we don't have anything else to do. | Planned for 3 hours | Sunday Apr.10 | To Do | Make changes to version three of manipulating.c and manipulating.h. Review with team once the changes have been made. Save the file in a new version folder. Make a back up of the files. Add the files to the folder so that it can be submitted by our project manager. | Delivery is measured: when we are satisfied with our project and it is up for final submission. | Planned for 3 hours | Monday Apr.11 | To Do
Sebastian (Tokenizing) | Made folders to put the different parts and versions of the project in | The project is considered delivered once we have submitted everything required in the folders and all files are in place ready to be checked | Planner Hours: 1.5 [Actual: 1.5] | Thursday Mar.31 | Done on time | Complete Version 1 of Tokenizing.c and Tokenizng.h. Review with team once this has been completed. Add comments to explain what certain specific lines of code do. | Deliverable is measured: files are submitted, compiling, and working as intended. Delivery Criteria is agreed if all files have been uploaded and there is nothing left to upload. | Planned Hours: 2.5 [Actual: 2.0] | Monday Apr.4 | Done | Make changes to Version 1 of Tokenizing.c and Tokenizing.h. Review and compile with the team once the changes have been made. Save the new version under the 'Version 2' folder. Log changes on git text file. | Deliverable is measured: Once my code and my group member's code is submitted by the deadline. The delivery criteria is agreed if we have submitted everything and no documents are left to be uploaded. | Planned Hours: 3.0 | Saturday Apr.9 | TO DO | Make changes to Version 2 of Tokenizing.c and Tokenizing.h. Review and compile with the team once the changes have been made. Save the new version under the 'Version 3' folder. Log changes on git text file. | Deliverable is measured: Once my code and my group member's code is submitted by the deadline. The delivery criteria is agreed if we have submitted everything and no documents are left to be uploaded. | Planned Hours: 3.0 | Sunday Apr.10 | TO DO | Make changes to Version 3 of Tokenizing.c and Tokenizing.h. Review and compile with the tema once the changes have been made. Save the new version under the 'Version 3.9' folder. Have the team make a backup of the files, submit files as needed. Add files to folders so they can be sent as a .zip file by the project manager. | Once Version 3 (Pro) has been submitted to the Professor, all items have been reviewed, code compiles, runs as expected with no bugs and mistakes. The delivery criteria is agreed if everything was submitted as planned and all the files as needed (.c, .c, .exe, and the .txt version control file, all submitted as a .zip) | Planned Hours: 4.0 | Monday Apr.11 | TO DO
Peter (Converting) | Organize group. Make first version of converting.c and make converting.h. Test if main.c compiles when encorporating each group member's v1 code | Deliverable is measured: if we all have our files available and they compile and all members are participating and aware of what to do. | Planned Hours: 2 [Actual Hours: 1.5] | Friday Apr.1 | Done on time(as of April 04, 2021) | Complete Version 1 of converting.c (including commenting out the code and refining logic that might look weird) and complete converting.h. Make conterting_test_cases.xlsx (shows elaborate + and - testing of my converting module). Post the output of my converting module into: converting_testing.txt . Complete main.c and insert comments into the file. Complete main_test_cases.xlsx (do simple tests unlike converting_test_cases.xlsx), and post the output of main_testing.txt (after everyone has submitted their .c files and .h files). Ensure that each group member has done what I stated above (with the exception of making main_test_cases.xlsx and main_testing.txt). Submit everyone's v1 files to BB in the form of a .zip and alert Professor Hesam where we have saved our final v1 files on Teams. | Deliverable is measured: if my group members and I submit our code on Teams. The delivery criteria agreed if we have something to submit to Blackboard. | Planned Hours: 1 .5[Actual Hours: 4.5] | Tuesday Apr.5 | DONE ON TIME | Complete Version 2 of converting.c (including commenting out the code and refining logic that might look weird) . Ensure that each group member has commented out their code and that version 2 compiles. Verify if Version 1 is acceptable by Professor's standards. Submit everyone's v2 files in the form of a .zip to Blackboard and Git. | Deliverable is measured: if my group members and I submit our code on Teams. The delivery criteria agreed if we have something to submit to Blackboard. | 3 planned hour ¦ N/A | Sunday Apr.10 | TO DO | Complete Version 3 of converting.c (including commenting out the code and refining logic that might look weird) . Ensure that each group member has commented out their code and that version 3 compiles. Verify if Version 2 is acceptable by Professor's standards. Submit everyone's v3 files in the form of a .zip to Blackboard and Git. | Deliverable is measured: if my group members and I submit our code on Teams. The delivery criteria agreed if we have something to submit to Blackboard. | 2 planned hour ¦ N/A | Monday Apr.11 | TO DO | If necessary, update Version 3 of converting.c (including commenting out the code and refining logic that might look weird) . Ensure that each group member has commented out their code and that version 3 compiles. Add or remove logic that would make our UI more pleasing. Submit everyone's v3 files in the form of a .zip to Blackboard and Git. | Deliverable is measured if all members contribut to the final submission and if the we agree on the final product. | 1 planned hour ¦ N/A | Monday Apr.11 | TO DO
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.